| CCMS V4 Key Dates and Deliverables Due Dates | Planned Due Date |
| --- | --- |
| Project Initiation | July 2007 |
| Initial User Interface Prototype and Logical Data Model Combination | October 2007 |
| Foundation Functional Design | October 2007 |
| Functional Design – Core Functionality | June 2008 |
| Functional Design for Data Exchanges and Functional Exposures via Integration Services Backbone (ISB) | July 2008 |
| Technical Design – Core Functionality with Data Exchanges and Functional Exposures via Integration Services Backbone | August 2008 |
| Functional Design for Portals | July 2008 |
| Functional Design for Statewide Reporting Data Warehouse | October 2008 |
| Technical Design – Portals and Statewide Reporting Data Warehouse | September 2008 |
| Construction – Core Functionality | January 2008 |
| Construction- Data Exchanges and Functional Exposures via ISB | February 2009 |
| Construction -Portals and Statewide Reporting Data Warehouse | May 2009 |
| System Testing -Core Functionality with Data Exchanges and Functional Exposures via Integration Services Backbone | April 2009 |
| System Testing - Portals and Statewide Reporting Data Warehouse | July 2009 |
| Integration Testing - Core Functionality with Data Exchanges and Functional Exposures via Integration Services Backbone | July 2009 |
| Stress Testing - Core Functionality with Data Exchanges and Functional Exposures via Integration Services Backbone | July 2009 |
| Stress Testing - Portals and Statewide Reporting Data Warehouse | November 2009 |
| Integration Testing - Portals and Statewide Data Warehouse | November 2009 |
| Product Acceptance Testing - Core Functionality with Data Exchanges and Functional Exposures via Integration Services Backbone | November 2009 |
| Product Acceptance Testing - Portals and Statewide Reporting Data Warehouse | February 2010 |

Appendix A6

CCMS V4 Application Development Key Dates