# Appendix A – Statement of Work

Table of Contents

Appendix A –  Statement of Work	i

A.A	Section A –  Introduction and Instructions	2

A.A.1	Statement of Work Overview	2

A.A.2	Instructions	2

A.B	Section B – Project Deliverables	3

A.B.1	Project Deliverables Overview	3

A.B.2	Instructions	3

A.C	Section C – Requirements and Business Solution Response Documentation	12

A.C.1	Requirements Overview	12

A.C.2	Instructions	12

A.D	Section D – Phoenix Program Glossary	17

A.D.1	General	17

A.D.2	Project Glossary Instructions	17

## Section A –  Introduction and Instructions

### Statement of Work Overview

As described in RFP Section VIII, Proposal Format, the Bidder must submit the required number of copies of the completed Statement of Work (SOW). The table below presents the sections of the Phoenix Program SOW to be incorporated from the Bidder’s Proposal. This SOW will be incorporated as Exhibit A into the Phoenix Program Agreement.

- Statement of Work

| Section | Description |
| --- | --- |
| A | Introduction and Instructions |
| B | Project Deliverables |
| C | Requirements and Business Solution Response Documentation |
| D | Phoenix Program Glossary |

### Instructions

The Statement of Work is not a stand-alone document, but complemented by other requirements and results in the completed Agreement. The following sections are descriptions of goods/services to be provided and are defined herein. Instructions to complete each section of the SOW are detailed in the following pages.

- Section A – Introduction and Instructions

No further input is required from the Bidder.

- Section B – Project Deliverables

This element of the Statement of Work shall reflect a deliverables–based, phased approach to the Phoenix Program Solution.

- Section C – Requirements Documents

This element of the Statement of Work shall contain all Requirements Documents required by the AOC for the Phoenix Program Solution. The Bidder must insert the specified requirement documents following the title pages provided in Section C.

- Section D – Phoenix Program Glossary

The Bidder must insert RFP Appendix G, Glossary into Section D.

## Section B – Project Deliverables

### Project Deliverables Overview

This section of the Statement of Work consists of all Project Deliverables for the Phoenix Program Solution.

### Instructions

The Bidder shall identify the individual Project Deliverables, as well as supporting information (e.g. frequency, review period) in Table A-2, Phoenix Program Deliverables.

The deliverables identified in Table A-2 shall be the same deliverable items identified by the AOC in RFP Appendix B-02, Implementation and Support Requirements, as well as additional deliverables proposed by Bidders.

- Phoenix Program Deliverables

| Deliv. # | Name of Deliverable | Proposal Reference | Acceptance Criteria | ASAP Phase | Upgrade Project | Optional New Functionality Projects | Optional Existing Functionality Projects |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Required Deliverables |  |  |  |  |  |  |  |
| 1 | Program Plan (consolidation of individual project plans) |  | - SOW Requirements - DED Content and Format Descriptions - AOC Approval in writing | All Phases | Yes | Yes | Yes |
| 2 | Project Plan |  |  | All Phases | Yes | Yes | Yes |
| 3 | Project Status Reports (including deliverable status reports, issues, risks, plan vs. actual status, etc.) |  |  | All Phases | Yes | Yes | Yes |
| 4 | Global Blueprint |  |  | Project Preparation | Yes | No | No |
| 5 | Communication Strategy |  |  | Project Preparation | Yes | No | No |
| 6 | Configured Hardware Environments (sandbox and development) |  |  | Project Preparation | Yes | Yes | Yes |
| 7 | End-User Training Strategy |  |  | Project Preparation | Yes | No | No |
| 8 | Issue Management and Resolution Strategy |  |  | Project Preparation | Yes | No | No |
| 9 | Project Charter |  |  | Project Preparation | Yes | Yes | Yes |
| 10 | Project Management Plan |  |  | Project Preparation | Yes | Yes | Yes |
| 11 | Project Scope Change Plan |  |  | Project Preparation | Yes | Yes | Yes |
| 12 | Quality Management Plan |  |  | Project Preparation | Yes | Yes | Yes |
| 13 | Business Process Organizational Change Management Strategy |  |  | Project Preparation | Yes | No | No |
| 14 | Risk Management Plan |  |  | Project Preparation | Yes | Yes | Yes |
| 15 | Master Test Strategy |  |  | Project Preparation | Yes | No | No |
| 16 | Training and Knowledge Transfer Strategy |  |  | Project Preparation | Yes | No | No |
| 17 | Business Intelligence Strategy |  |  | Business Blueprint | Yes | No | No |
| 18 | Business Process Fit/Gap Analysis |  |  | Business Blueprint | Yes | Yes | Yes |
| 19 | Business Process Organizational Change Management Plan |  |  | Business Blueprint | Yes | Yes | Yes |
| 20 | Data Conversion Strategy |  |  | Business Blueprint | Yes | No | No |
| 21 | Detailed Design Standards and Design Documents |  |  | Business Blueprint | Yes | Yes | No |
| 22 | Detailed Functional and Technical Specifications, including requirements documents, use cases, and logical, data flow diagrams, architecture documents and physical data models |  |  | Business Blueprint | Yes | Yes | Yes |
| 23 | Detailed Reports, Interfaces, Conversions, Enhancements, and Forms (RICEF) Development Schedule |  |  | Business Blueprint | Yes | Yes | Yes |
| 24 | Blueprint |  |  | Business Blueprint | Yes | Yes | Yes |
| 25 | End-User Training Plans |  |  | Business Blueprint | Yes | Yes | Yes |
| 26 | Integration, User Acceptance, Regression, and Security Test Plans |  |  | Business Blueprint | Yes | Yes | Yes |
| 27 | Operational and Technical Assessment and Current Environment Analysis Results (including Capacity Plan) |  |  | Business Blueprint | Yes | Yes | Yes |
| 28 | Software Configuration Management Policies and Procedures |  |  | Business Blueprint | Yes | Yes | Yes |
| 29 | Stress Testing Strategy |  |  | Business Blueprint | Yes | No | No |
| 30 | System Landscape, Technical and Business Design Strategy |  |  | Business Blueprint | Yes | No | No |
| 31 | System Security Strategy |  |  | Business Blueprint | Yes | No | No |
| 32 | Technical System Design Document |  |  | Business Blueprint | Yes | Yes | Yes |
| 33 | Test Cases and Test Data |  |  | Business Blueprint | Yes | Yes | Yes |
| 34 | Integration, Parallel and User Acceptance Test Plans |  |  | Business Blueprint | Yes | Yes | Yes |
| 35 | Test Scripts |  |  | Business Blueprint | Yes | Yes | Yes |
| 36 | Training and Knowledge Transfer Plans |  |  | Business Blueprint | Yes | Yes | Yes |
| 37 | Vendor Response to SAP QA Review |  |  | Business Blueprint | Yes | Yes | Yes |
| 38 | Training Curriculum Document |  |  | Business Blueprint | Yes | Yes | Yes |
| 39 | Business Continuity Strategy |  |  | Realization | Yes | No | No |
| 40 | Business Intelligence Plan |  |  | Realization | Yes | Yes | Yes |
| 41 | Communication Plan |  |  | Realization | Yes | Yes | Yes |
| 42 | Data Conversion Plan |  |  | Realization | Yes | Yes | Yes |
| 43 | Documented Successful Testing Results |  |  | Realization | Yes | Yes | Yes |
| 44 | Draft Training Materials |  |  | Realization | Yes | Yes | Yes |
| 45 | Organizational Readiness Assessment |  |  | Realization | Yes | Yes | Yes |
| 46 | Stress Test Plan |  |  | Realization | Yes | Yes | Yes |
| 47 | System and User Documentation |  |  | Realization | Yes | Yes | Yes |
| 48 | System Security Plan |  |  | Realization | Yes | Yes | Yes |
| 49 | Training and Knowledge Transfer Effectiveness Reports |  |  | Realization | Yes | No | Yes |
| 50 | Vendor Response to SAP QA Review |  |  | Business Blueprint | Yes | Yes | Yes |
| 51 | Batch Schedule |  |  | Final Preparation | Yes | Yes | Yes |
| 52 | Business Contingency Plan |  |  | Final Preparation | Yes | Yes | Yes |
| 53 | Business Continuity Plan |  |  | Final Preparation | Yes | Yes | Yes |
| 54 | Final Training Materials |  |  | Final Preparation | Yes | Yes | Yes |
| 55 | Go Live Checklist |  |  | Final Preparation | Yes | No | Yes |
| 56 | Initial Detailed Deployment Plan |  |  | Final Preparation | Yes | Yes | Yes |
| 57 | Maintenance Repair Policies and Procedures |  |  | Final Preparation | Yes | No | No |
| 59 | Post Production Support Strategy |  |  | Final Preparation | Yes | No | Yes |
| 60 | Recommended Operations and Administration Procedures |  |  | Final Preparation | Yes | Yes | Yes |
| 61 | Role to Position Mapping |  |  | Final Preparation | Yes | Yes | Yes |
| 62 | Site-specific Training Materials |  |  | Final Preparation | Yes | Yes | Yes |
| 63 | Site-specific Transition Plans |  |  | Final Preparation | Yes | Yes | Yes |
| 64 | Systems Maintenance Plan |  |  | Final Preparation | Yes | Yes | No |
| 65 | Technical Documentation (including technical and architectural specifications, etc.) |  |  | Final Preparation | Yes | Yes | Yes |
| 66 | Training (includes support staff training and knowledge transfer) |  |  | Final Preparation | Yes | Yes | Yes |
| 67 | Training (includes user training and knowledge transfer) |  |  | Final Preparation | Yes | Yes | Yes |
| 68 | Go/No-go Meeting and Go/No-go Documentation |  |  | Final Preparation | Yes | Yes | Yes |
| 69 | Vendor Response to SAP QA Review |  |  | Final Preparation | Yes | Yes | Yes |
| 70 | Deployment Roadmaps |  |  | Go Live & Deployment Support | Yes | Yes | Yes |
| 71 | Final Detailed Deployment Plan |  |  | Go Live & Deployment Support | Yes | No | Yes |
| 72 | Maintenance Production Release Plans |  |  | Go Live & Deployment Support | Yes | No | Yes |
| 73 | Organizational Change Management Effectiveness Assessment |  |  | Go Live & Deployment Support | Yes | No | Yes |
| 74 | Phase Closeout (to include System Tuning, Knowledge Transfer Assessment, Project Artifacts in Repository, Lessons Learned, Update Blueprint, and Transition Support to COE and Shared Services |  |  | Go Live & Deployment Support | Yes | No | Yes |
| 75 | Service Level Performance Reports |  |  | Go Live & Deployment Support | Yes | No | Yes |
| 76 | Successful Deployment Documented |  |  | Go Live & Deployment Support | Yes | No | Yes |
| Additional Deliverables Proposed by Bidders |  |  |  |  |  |  |  |
| 77 |  |  |  |  |  |  |  |
| 78 |  |  |  |  |  |  |  |
| 79 |  |  |  |  |  |  |  |

Per RFP requirements (see RFP Appendix B-02, Implementation and Support Requirements), the Contractor must develop Project Deliverables in the form and format agreed to by the AOC and Contractor using the Deliverables Expectations Document (DED), and approved by the AOC. No work will be performed on any deliverable associated with a payment milestone until the DED has been approved in writing by the AOC. As each Project Deliverable is submitted, the Contractor must include a copy of the Project Deliverable’s Expectation Document as the cover sheet. See Figure A-1 below for a template to be used for Deliverable Expectations Document during projects.

- As part of their Proposals, Bidders must provide DED for following “Project Preparation Phase” deliverables defined within the RFP, using the DED template in Figure A-2.  Submission of DEDs for these deliverables will be evaluated as part of the Bidder Solution.

- Deliverables for which the Bidder has to complete a DED within Proposal

| Deliverable # | Name of Deliverable |
| --- | --- |
| 4 | Global Blueprint |
| 5 | Communication Strategy |
| 7 | End-User Training Strategy |
| 10 | Project Management Plan |
| 12 | Quality Management Plan |
| 13 | Business Process Organizational Change Management Strategy |
| 14 | Risk Management Plan |
| 15 | Master Test Strategy |
| 16 | Training and Knowledge Transfer Strategy |
| 22 | Detailed Functional and Technical Specifications, including requirements documents, use cases, and logical, data flow diagrams, architecture documents and physical data models |
| 24 | Blueprint |

- Template of Project Deliverable Expectation Document (Bidder to Repeat for Each Required DED Above)

| Project Deliverable Expectations Document |  |
| --- | --- |
| Project Deliverable Number: | Title of Deliverable: <Insert> |
| Proposal Reference: <Insert> | Contract Reference: |
| Frequency: <Insert> | Draft Submission Due: <Insert> |
| State’s Draft Review and Comment Period: XX Days | Final Submission Due: XX Days after receipt of draft comments |
| Approval Required: Yes/No | Distribution: AOC PM – one hard copy and one soft copy Project Oversight Contractor – one soft copy |
| Contractor: Complete shaded area below |  |
| Prepared by (please print): | Date Submitted: |
| Date Submitted 2: | Date Submitted 3: |
| Phone Number: | FAX: |
| E-mail: |  |
| Deliverable Acceptance Criteria (include SOW requirements (and or requirement modifications agreed to by AOC through operational change processes), format and content description provided by Contractor related to deliverable as agreed to by AOC). <Insert Proposed Format and Content Description for Each Required DED> |  |
| AOC Approval/Comments |  |
| Approved by: | Date: |
| Signature: |  |
| Comments: |  |

## Section C – Requirements and Business Solution Response Documentation

### Requirements Overview

This section of the Statement of Work consists of all Requirements and Bidder Approach Documentation for the Phoenix Program.

### Instructions

The Bidder must insert the following specified Requirements and Business Solution Response Documentation following the title pages provided in Section C below. Each of the title pages refers to the specific requirement for that document as specified in the RFP and provided in the Bidder’s Final Proposal.

- Administrative Requirements - Responses to every requirement in RFP Section V, Administrative Requirements, including all completed forms contained in RFP Appendix C, Bid Response Forms.

- Non-Functional and Functional Requirements - Responses to every requirement in RFP Section VI.2, Non-Functional and Functional Requirements, and RFP Appendix B,  Requirements Response Matrices.

- Project Staff and Project Organization Bidder Responses - Responses to every Bidder experience and project staff organization response requirements in RFP Section VI.3, Project Staff and Project Organization Response Requirements.

- Business Solution Bidder Responses - Responses to every functional, technical, implementation and maintenance and support approach response requirements in RFP Section VI.4, Business Solution Response Requirements.

Administrative Requirements

Nonfunctional and Functional Requirements

Project Staff and Project Organization Response

Business Solution Response Requirements

## Section D – Phoenix Program Glossary

### General

This section of the Statement of Work contains the Phoenix Program Glossary defined in Appendix G, Glossary, of the RFP.

### Project Glossary Instructions

The Bidder must insert the Phoenix Program Glossary as defined in RFP Appendix H, Glossary.

Phoenix Program Glossary